## Sheet1
HC 900 controller | 7175
Control Station & Software | 3505
Thermocouples | 500
Pressure transducers | 1500
Temperature display | 3300
West & North gate actuators | 300
copper tubing - pressure sensors | 360
Electrical Cabinet | 2200
Wiring | 215
Conduit | 50
Ceramic tube insert | 100
Replacement damper & actuator | 400
John Clause Labor | 4000
Total | 23605
Weeks
Project Submission/Approval | 1
Part Lead Time | 5
Installation | 3
Rotary kiln pressure control testing | 4
Training | 1 |  | Inst
Dryer system control testing | 6
Training | 1
Total | 21 | weeks
Project Risks | Response
Controller Setup Improperly | Work closely with John Clause to ensure proper implementation. Confer with Tim Hastings as back-up check.
Negative Impact on Production | Almost impossible, as we are manually managing process control now (poorly.) Worst case is controller failure after comissioning. In this worst case, we can always go back to manual control.
Delay of Project Implementation due to maintenance unavailability | Option to outsource electrical work. Will add cost to the project. Alternatively, accept delays
Delay of Project due to production not running | This is a reality we must accept. Will work with Chandra to give input on best times to run for project, but ultimately production comes first.